## Milestone Chart in Excel
Date | Activity | Date | Activity | Text Placement
9 April, 2019 | Proposal | 9 April, 2019 | Proposal | 10
8 May, 2019 | Analysis | 8 May, 2019 | Analysis | -10
3 June, 2019 | Design | 3 June, 2019 | Design | 10
24 June, 2019 | Implementation | 24 June, 2019 | Implementation | -10
1 July, 2019 | Testing | 1 July, 2019 | Testing | 10
12 July, 2019 | Final Documentation | 12 July, 2019 | Final Documentation | -10
Milestone Chart in Excel